Lab 2: EPICs & User Stories - Podcast Guest Scheduling & Outline Builder

Aryan Upadhyay  |  SRN: PES1UG25CS806  |  Section C  |  Software Engineering (UE24CS341A)

Jira project: Podcast-Guest-Scheduler (key PGS), Scrum template, company-managed. Built from the Lab 1 requirements for Problem Statement #60. The same items are in jira_import.csv for Jira's CSV import.

1. Epics

| Key | Epic | Description | Lab 1 requirements |
| --- | --- | --- | --- |
| E1 | Epic 1: Host Availability Management | Let show hosts publish recording slots in their time zone and block dates they are unavailable. | FR-002 |
| E2 | Epic 2: Guest Booking & Calendar Invites | Let guests book an interview slot through a secure link and get a calendar invite automatically. | FR-001, FR-003, NFR-002 |
| E3 | Epic 3: Guest Outline Collection | Collect structured talking points and biography links from guests and organise them on an episode board. | FR-001, FR-004 |
| E4 | Epic 4: Run-of-Show Production Notes | Turn the episode board into a timestamped run-of-show and export it as a PDF production sheet. | FR-005, NFR-001 |

2. User Stories (prioritised backlog)

Epic 1: Host Availability Management

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 1.1: Publish Time Slots | As a show host | I want to publish recording slots with date, start time and duration | So that guests can only book times I have offered | High | 3 | Sprint 1 |
| Story 1.2: Block Dates | As a show host | I want to block dates when I am unavailable | So that no guest can book me on those days | High | 2 | Sprint 1 |
| Story 1.3: Time-Zone Display | As a podcast guest | I want to see open slots in my own time zone | So that I do not turn up at the wrong hour | Medium | 3 | Backlog |

Epic 2: Guest Booking & Calendar Invites

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 2.1: Book Interview Slot | As a podcast guest | I want to pick an open slot from the host's booking page | So that my interview is confirmed without email back-and-forth | Highest | 5 | Sprint 1 |
| Story 2.2: Calendar Invites | As a podcast guest | I want to receive a calendar invite as soon as I book | So that the recording is in my calendar with the link | High | 5 | Sprint 1 |
| Story 2.3: Join Waitlist | As a podcast guest | I want to join a waitlist when no slots are open | So that I am told when the host adds new times | Low | 3 | Backlog |
| Story 2.4: Secure Booking Links | As a show host | I want booking links to be unguessable and expire after use or 14 days | So that strangers cannot book fake interviews or read guest details | High | 3 | Sprint 2 |

Epic 3: Guest Outline Collection

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 3.1: Submit Talking Points | As a podcast guest | I want to submit 3-10 bullet-point discussion topics when I book | So that the host knows what I want to talk about | High | 3 | Sprint 1 |
| Story 3.2: Add Biography Links | As a podcast guest | I want to add links to my bio and past work | So that the host can introduce me properly | Medium | 1 | Sprint 2 |
| Story 3.3: Episode Board | As a show host | I want to see all guest outlines on one board and reorder topics | So that I can plan the flow of the episode | Medium | 5 | Sprint 2 |

Epic 4: Run-of-Show Production Notes

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 4.1: Timestamped Run-of-Show | As a show host | I want start times to be calculated from each segment's planned duration | So that I know exactly when each topic starts during recording | High | 5 | Sprint 2 |
| Story 4.2: PDF Production Sheet | As a show host | I want to export the run-of-show as a PDF in under 1 second | So that I can share it with my producer right before recording | High | 3 | Sprint 2 |

3. Story Points (Fibonacci) - Planning Poker estimates

Points use the Fibonacci scale (1, 2, 3, 5, 8...) relative to the smallest story (3.2 Add Biography Links = 1). Each story was estimated Planning-Poker style: pick a card for complexity, amount of work and uncertainty, compare with already-estimated stories, and settle on one value.

| Story | Points | Why |
| --- | --- | --- |
| 1.1 Publish Time Slots | 3 | Simple form + slot table; well understood. |
| 1.2 Block Dates | 2 | Flag on top of 1.1 plus a booking check. |
| 1.3 Time-Zone Display | 3 | Time-zone conversion and edge cases (DST). |
| 2.1 Book Interview Slot | 5 | Slot holds and double-booking race conditions. |
| 2.2 Calendar Invites | 5 | External calendar API integration; most uncertainty. |
| 2.3 Join Waitlist | 3 | Notification trigger on new slots. |
| 2.4 Secure Booking Links | 3 | Token generation, expiry and access checks. |
| 3.1 Submit Talking Points | 3 | Structured form with validation. |
| 3.2 Add Biography Links | 1 | Two URL fields with validation. |
| 3.3 Episode Board | 5 | Drag-and-drop UI plus saving order and history. |
| 4.1 Timestamped Run-of-Show | 5 | Timing logic and segment model. |
| 4.2 PDF Production Sheet | 3 | PDF library + performance benchmark. |

Total backlog: 41 points.

4. Sprint Plan (1-week sprints)

| Sprint | Goal | Stories | Points |
| --- | --- | --- | --- |
| PGS Sprint 1 | A host can publish slots and a guest can book one, submit talking points and receive a calendar invite. | 1.1, 1.2, 2.1, 2.2, 3.1 | 18 |
| PGS Sprint 2 | Secure the booking links, give the host the episode board, and produce the timestamped PDF run-of-show. | 2.4, 3.2, 3.3, 4.1, 4.2 | 17 |
| Backlog | Carried to a later sprint. | 1.3, 2.3 | 6 |

Workflow for each sprint: start sprint -> move stories To Do -> In Progress -> Done in priority order -> Complete sprint -> Reports > Burndown Chart.