Lab 2: Agile Backlog & Sprint Simulation (Jira) - Podcast Guest Scheduling & Outline Builder

Aryan Upadhyay  |  SRN: PES1UG25CS806  |  Section C  |  Software Engineering (UE24CS341A)

Jira project: Podcast-Guest-Scheduler (key PGS), Scrum template, company-managed. The Epics and User Stories below come from the Lab 1 requirements for Problem Statement #60. A ready-to-import file (jira_import.csv) with the same items is included in this folder.

1. Epics

| Key | Epic | Description | Lab 1 requirements |
| --- | --- | --- | --- |
| E1 | Epic 1: Host Availability Management | Let show hosts publish recording slots in their time zone and block dates they are unavailable. | FR-002 |
| E2 | Epic 2: Guest Booking & Calendar Invites | Let guests book an interview slot through a secure link and get a calendar invite automatically. | FR-001, FR-003, NFR-002 |
| E3 | Epic 3: Guest Outline Collection | Collect structured talking points and biography links from guests and organise them on an episode board. | FR-001, FR-004 |
| E4 | Epic 4: Run-of-Show Production Notes | Turn the episode board into a timestamped run-of-show and export it as a PDF production sheet. | FR-005, NFR-001 |

2. User Stories (prioritised backlog)

Epic 1: Host Availability Management

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 1.1: Publish Time Slots | As a show host | I want to publish recording slots with date, start time and duration | So that guests can only book times I have offered | High | 3 | Sprint 1 |
| Story 1.2: Block Dates | As a show host | I want to block dates when I am unavailable | So that no guest can book me on those days | High | 2 | Sprint 1 |
| Story 1.3: Time-Zone Display | As a podcast guest | I want to see open slots in my own time zone | So that I do not turn up at the wrong hour | Medium | 3 | Backlog |

Epic 2: Guest Booking & Calendar Invites

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 2.1: Book Interview Slot | As a podcast guest | I want to pick an open slot from the host's booking page | So that my interview is confirmed without email back-and-forth | Highest | 5 | Sprint 1 |
| Story 2.2: Calendar Invites | As a podcast guest | I want to receive a calendar invite as soon as I book | So that the recording is in my calendar with the link | High | 5 | Sprint 1 |
| Story 2.3: Join Waitlist | As a podcast guest | I want to join a waitlist when no slots are open | So that I am told when the host adds new times | Low | 3 | Backlog |
| Story 2.4: Secure Booking Links | As a show host | I want booking links to be unguessable and expire after use or 14 days | So that strangers cannot book fake interviews or read guest details | High | 3 | Sprint 2 |

Epic 3: Guest Outline Collection

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 3.1: Submit Talking Points | As a podcast guest | I want to submit 3-10 bullet-point discussion topics when I book | So that the host knows what I want to talk about | High | 3 | Sprint 1 |
| Story 3.2: Add Biography Links | As a podcast guest | I want to add links to my bio and past work | So that the host can introduce me properly | Medium | 1 | Sprint 2 |
| Story 3.3: Episode Board | As a show host | I want to see all guest outlines on one board and reorder topics | So that I can plan the flow of the episode | Medium | 5 | Sprint 2 |

Epic 4: Run-of-Show Production Notes

| Story | As a | I want to | So that | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| Story 4.1: Timestamped Run-of-Show | As a show host | I want start times to be calculated from each segment's planned duration | So that I know exactly when each topic starts during recording | High | 5 | Sprint 2 |
| Story 4.2: PDF Production Sheet | As a show host | I want to export the run-of-show as a PDF in under 1 second | So that I can share it with my producer right before recording | High | 3 | Sprint 2 |

3. Story Points (Fibonacci) and Estimation Rationale

Points use the Fibonacci scale (1, 2, 3, 5, 8...) relative to the smallest story (3.2 Add Biography Links = 1). Each story was estimated Planning-Poker style: pick a card for complexity, amount of work and uncertainty, then compare with already-estimated stories before settling on a value.

| Story | Points | Why |
| --- | --- | --- |
| 1.1 Publish Time Slots | 3 | Simple form + slot table; well understood. |
| 1.2 Block Dates | 2 | Flag on top of 1.1 plus a booking check. |
| 1.3 Time-Zone Display | 3 | Time-zone conversion and edge cases (DST). |
| 2.1 Book Interview Slot | 5 | Slot holds and double-booking race conditions. |
| 2.2 Calendar Invites | 5 | External calendar API integration; most uncertainty. |
| 2.3 Join Waitlist | 3 | Notification trigger on new slots. |
| 2.4 Secure Booking Links | 3 | Token generation, expiry and access checks. |
| 3.1 Submit Talking Points | 3 | Structured form with validation. |
| 3.2 Add Biography Links | 1 | Two URL fields with validation. |
| 3.3 Episode Board | 5 | Drag-and-drop UI plus saving order and history. |
| 4.1 Timestamped Run-of-Show | 5 | Timing logic and segment model. |
| 4.2 PDF Production Sheet | 3 | PDF library + performance benchmark. |

Total backlog: 41 points.

4. Sprint Plan (1-week sprints)

| Sprint | Goal | Stories | Points |
| --- | --- | --- | --- |
| PGS Sprint 1 | A host can publish slots and a guest can book one, submit talking points and receive a calendar invite. | 1.1, 1.2, 2.1, 2.2, 3.1 | 18 |
| PGS Sprint 2 | Secure the booking links, give the host the episode board, and produce the timestamped PDF run-of-show. | 2.4, 3.2, 3.3, 4.1, 4.2 | 17 |
| Backlog | Carried to a later sprint. | 1.3, 2.3 | 6 |

Workflow for each sprint: start sprint -> move stories To Do -> In Progress -> Done in priority order -> Complete sprint -> check Reports > Burndown Chart.

5. Screenshots

Saved in the screenshots/ folder: (1) backlog with Epics and User Stories, (2) story point assignments, (3) active sprint board, (4) burndown chart for each sprint.

6. Reflection

1. Did your estimations reflect the actual effort? Mostly. The external calendar integration (2.2, 5 points) and slot booking with holds (2.1, 5 points) carried the most uncertainty and stayed In Progress longest. Small form stories such as 1.2 Block Dates and 3.2 Biography Links moved to Done quickly, matching their 1-2 point estimates. Time-zone handling (1.3) was the story most likely to be underestimated because of daylight-saving edge cases.

2. Was your backlog well-prioritised? Yes. Sprint 1 holds only what is needed for one complete booking: publish slots, block dates, book a slot, submit talking points, and send the invite. The host-side production features (episode board, run-of-show, PDF) and link security followed in Sprint 2, and nice-to-have items (waitlist, time-zone display) stayed in the backlog.

3. How did your simulated sprint align with your plan? Both sprints were completed with all committed stories Done (18 points in Sprint 1, 17 points in Sprint 2). Because the sprint was simulated, stories were moved in priority order rather than over real working days, so the order of completion matched the plan.

4. What insights did the burndown chart give about your team's capacity? The remaining-work line dropped in steps as each story moved to Done. The 5-point stories caused the biggest single drops, so splitting them (for example, separating slot holds from the booking form) would give a smoother, more predictable burndown. The two sprints suggest a velocity of about 18 points per week, so the remaining 6 points fit easily into Sprint 3.